## Login Use
Spring CLC | Project Name: | Spring CLC | Test designed date: | 2019-11-10
| Module Name: | Log In | Test execution date: | 2019-11-10
| Release Version: | 5
Pre-Condition | A user has already registerered to use the application
Dependencies: | N/A
Test Priority | High
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Log In | A user can sucessfully log in without issue using a created username and password | Enter username into username field and password into password field | Username: Msillanp, Password: password | User is logged in and returned to the main page | User is stored in session and main page is displayed | User is logged in and returned to the main page | Pass

## Login Validation
Spring CLC | Project Name: | Spring CLC | Test designed date: | 2019-11-10
| Module Name: | Log In | Test execution date: | 2019-11-10
| Release Version: | 5
Pre-Condition | N/A
Dependencies: | N/A
Test Priority | Medium
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Log In Blank Form | A user can not attempt to log in using a blank form | Click the login button without filling out fields | N/A | Validation messages are returned on both fields | N/A | Validation messages are returned on both fields | Pass
2 | Log In Incorrect Length | A user can not attempt to log in using fields on invalid lengths | Enter a username of more than 14 characters and a password of less than 7 characters | Username: 123456789123456789 Password: pass | Validation messages are returned on both fields | N/A | Validation messages are returned on both fields | Pass

## Registration Use
Spring CLC | Project Name: | Spring CLC | Test designed date: | 2019-11-10
| Module Name: | Registration | Test execution date: | 2019-11-10
| Release Version: | 5
Pre-Condition | N/A
Dependencies: | Functional Link on Login Page
Test Priority | High
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Register | A User is able to register to use the application | 1.Click the "New to SpringCLC?" link on login page 2. Fill out the fields on the form Click the 'register' button | First Name: John Last Name: Smith Username: Jsmith Password: password Email: Jsmith@Gmail.com Phone Number: 111-222-3333 | User is registered and returned to the login page | User appears in database and login page is displayed | User is registered and returned to the login page | pass

## Registration Validation
Spring CLC | Project Name: | Spring CLC | Test designed date: | 2019-11-10
| Module Name: | Registration | Test execution date: | 2019-11-10
| Release Version: | 5
Pre-Condition | User has navigated to the registration page
Dependencies: | Functional Link on Login Page
Test Priority | Medium
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Register Blank Form | A user cannot submit a blank registration form | 1. Click the 'sign up' button without filling out any fields | N/a | Validation messages are returned on all fields | N/A | Validation messages are returned on all fields | pass
2 | Incorrect Field Length | A user cannot submit a form with fields that are too long or short | 1. Fill out 'First Name', 'Last Name', 'Username', and 'Password' fields with only one letter 2. Submit the form using the 'sign up' button | First Name: a Last Name: b Username: c Password: d | Validation messages are returned on all fields | N/A | Validation messages are returned on all fields | pass
3 | Invalid Field Input | A user cannot submit a form with an invalid email or phone number | 1. Fill out the email form with plain text, number, or other non-email format 2. Fill out the phone number without dashes, with other special characters, or invalid length | Email: Hello@world@website.com Phone number: 111-222-3333-44444 | Validation messages are returned on invalid fields | N/A | Validation messages are returned on invalid fields | pass

## Album Use
Spring CLC | Project Name: | Spring CLC | Test designed date: | 2019-11-10
| Module Name: | Album | Test execution date: | 2019-11-10
| Release Version: | 5
Pre-Condition | A user has logged in and navigated to the library page
Dependencies: | This module relies on a valid user logging in and a valid user ID being stored in the session
Test Priority | high
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Album Creation | An album can be successfully created by a valid user | 1. Press the "Add Album" button to open the modal 2. Fill out the Name, Artist, Description, and Genre fields 3.Click "Create Album" | Name: NewAlbum Artist: NewArtist Description: Hello World Genre: Music | Album is created and appears in library | Album exists in database and is able to be selected | Album is created and appears in library | pass
2 | Album View | An existing album can be examined by a user | Click on a created album | Name: NewAlbum | An album details page is displayed with further options | N/A | An album details page is displayed with further options | pass
3 | Album Update | An existing album can be updated by a user | 1. Click on the album to be updated 2. Click on the "edit album" button 3. Change any information 4. Click the "edit album" button | Change Artist: NewArtist to Artist: NewerArtist | Updated information is displayed on the album page | Album is updated in the database and the updated album is viewable | Updated information is displayed on the album page | pass
4 | Album Delete | An existing album can be deleted by a user | 1. Click on the album to be deleted 2. Click on the "Delete Album" button 3. Confirm deletion in the dialog | Delete any existing album | Album is removed and no longer visible or accessible | Album is no longer in the database or app | Album is removed and no longer visible or accessible | pass

## Album Validation
Spring CLC | Project Name: | Spring CLC | Test designed date: | 2019-11-10
| Module Name: | Album | Test execution date: | 2019-11-10
| Release Version: | 5
Pre-Condition | A user has logged in and navigated to the library page
Dependencies: | This module relies on a valid user logging in and a valid user ID being stored in the session
Test Priority | medium
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Add Album Blank Form | A new album cannot be submitted with no data | 1. Press the 'Add Album' Button 2. Submit the form without filling out fields | N/A | Validation messages are returned on all fields | N/A | Validation messages are returned on all fields | pass
2 | Add Album Invalid Length | A new Album cannot be submitted with invalid field length | 1. Click on the "Add album" button 2. Fill out every field with 45 characters 3. Click the "add album" button | All Forms: 123456789123456789123456789123456789123456789 | Validation messages are returned on all fields | N/A | Validation messages are returned on all fields | pass
3 | Update Album Blank Form | An updated album cannot be submitted with no data | 1. Press the 'Edit Album' Button 2. Submit the form without filling out fields | N/A | Validation messages are returned on all fields | N/A | Validation messages are returned on all fields | pass
2 | Update Album Invalid Length | An updated cannot be submitted with invalid field length | 1. Click on the album to be updated 2. Click on the "edit album" button 3. Fill out every field with 45 characters 4. Click the "edit album" button | All Forms: 123456789123456789123456789123456789123456789 | Validation messages are returned on all fields | N/A | Validation messages are returned on all fields | pass

## Song Use
Spring CLC | Project Name: | Spring CLC | Test designed date: | 2019-11-10
| Module Name: | Song | Test execution date: | 2019-11-10
| Release Version: | 5
Pre-Condition | A valid album has been created, and a user is at that album's page
Dependencies: | The album module must be completely functional, as a song can't be added without the context of an album
Test Priority | High
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Song Creation | A song can be added to an existing album | 1. In an existing album, click the "add song" button on the top right of the album details page 2. Fill out the artist and title 3. Click the "Add song" button | Title: Song 1 Artist: Michael | The song is created and added to the list of track on the album | The song is visible within the database with an albums_ID matching the album | The song is created and added to the list of track on the album | pass
2 | Song Update | An existing track can have its information edited | 1. Press the gear icon next to a listed song 2. Change any information 3. Press the "edit song" button | Change Artist: Michael to Artist: Brady | The song artist is updated (This can be viewed by clicking the gear again) | The song is visible within the database with updated info | The song artist is updated (This can be viewed by clicking the gear again) | pass
3 | Song Deletion | An existing track can be removed from an album | 1. Press the 'x' icon next to a listed song 2. Confirm deletion on the dialog by pressing 'remove' | Delete any track from any album | The song is removed and no longer visible | The song is no longer visible in the database or in the application | The song is removed and no longer visible | pass

## Song Validation
Spring CLC | Project Name: | Spring CLC | Test designed date: | 2019-11-10
| Module Name: | Song | Test execution date: | 2019-11-10
| Release Version: | 5
Pre-Condition | A valid album has been created, and a user is at that album's page
Dependencies: | The album module must be completely functional, as a song can't be added without the context of an album
Test Priority | Medium
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Add Album Blank Form | A new album cannot be submitted with no data | 1. In an existing album, click the "add song" button on the top right of the album details page 2. Click the "Add song" button without filling out fields | N/A | Validation messages are returned on both fields | N/A | Validation messages are returned on all fields | pass
2 | Add Album Invalid Length | A new Album cannot be submitted with invalid field length | 1. In an existing album, click the "add song" button on the top right of the album details page 2. Fill out both fields with 45 characters 3. Click the "Add song" button | All Forms: 123456789123456789123456789123456789123456789 | Validation messages are returned on both fields | N/A | Validation messages are returned on all fields | pass
3 | Update Album Blank Form | An updated album cannot be submitted with no data | 1. Press the gear icon next to a listed song 2. Press the "edit song" button without filling out fields | N/A | Validation messages are returned on both fields | N/A | Validation messages are returned on all fields | pass
2 | Update Album Invalid Length | An updated cannot be submitted with invalid field length | 1. Press the gear icon next to a listed song 2. Fill out both fields with 45 characters 3. Press the "edit song" button | All Forms: 123456789123456789123456789123456789123456789 | Validation messages are returned on both fields | N/A | Validation messages are returned on all fields | pass